## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Task Owner | Start Date | Due Date | Duration | Notes | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone 1 - Project Initiation
Align and evaluate stakeholders | Peta |  |  | 3 | bar: WEEK 1 M to WEEK 1 W
Calculate projections and enhancements | Peta, Gilly, Alex, Seydou |  |  | 2 | bar: WEEK 1 T to WEEK 1 W
Meet with staff and gather historical data on ordering process | Peta, Gilly, Alex |  |  | 1 | bar: WEEK 1 W
Create project charter | Peta |  |  | 3 | bar: WEEK 1 W to WEEK 1 F
Schedule kick-off meeting | Peta |  |  | 1 | bar: WEEK 1 R
Milestone 2 - Tablet Sourcing
Research tablet customizations options | Seydou |  |  | 4 | Must be compatible with current operating system | bar: WEEK 1 R to WEEK 2 T
Obtain quotes for tablets | Deanna |  |  | 3 | bar: WEEK 1 F to WEEK 2 T
Choose tablet system | Seydou |  |  | 2 | bar: WEEK 2 T to WEEK 2 W
Determine quantity to order for each location & if/how many backups are needed | Alex, Gilly, Seydou |  |  | 1 | bar: WEEK 2 W
Select top 3 vendors for branding | Deanna, Seydou |  |  | 1 | bar: WEEK 2 W
Create contracts and SoW's for vendors | Deanna |  |  | 4 | bar: WEEK 2 W to WEEK 3 M
Finalize contracts and SoW's | Deanna |  |  | 2 | bar: WEEK 2 F to WEEK 3 M
Phase 1 progress meeting | Peta |  |  | 1 | bar: WEEK 2 W
Milestone 3 - General Project Planning
Announce launch date via email to stakeholders | Peta |  |  | 1 | bar: WEEK 3 T
Project plan updates | Peta |  |  | 13 | bar: WEEK 3 T to WEEK 5 R
Outline design drafts dates | Seydou |  |  | 2 | bar: WEEK 3 T to WEEK 3 W
Create initial launch day plan | Deanna |  |  | 2 | bar: WEEK 3 T to WEEK 3 W
Create post-dining survey to assess customer satisfaction & establish metrics | Peta |  |  | 3 | bar: WEEK 3 W to WEEK 3 F
Phase 2 progress meeting | Peta |  |  | 1 | bar: WEEK 5 R
Milestone 4 - Finalizing Tablets
Create mockup for menu layout with coupon links | Carter |  |  | 5 | bar: WEEK 4 M to WEEK 4 F
Finalize custom branding, design, menu item upload with vendor | Seydou |  |  | 3 | bar: WEEK 4 R to WEEK 5 M
Order 2 sample tablets for test run | Deanna |  |  | 10 | Shipping is 7-10 business days + installation time of 4 hours | bar: WEEK 5 M to WEEK 6 F
Confirm tablet arrival, quality, and layout | Seydou |  |  | 1 | bar: WEEK 6 W
Schedule electrician for test installation | Deanna |  |  | 1 | bar: WEEK 6 W
Test sample tablets & determine bar installation location w/ GMs | Seydou |  |  | 1 | bar: WEEK 6 W
Install sample tablets and identify potential issues | Seydou |  |  | 1 | bar: WEEK 6 W
Finalize final order for remaining tablets with vendor | Deanna |  |  | 10 | Shipping is 7-10 business days + installation time of 4 hours | bar: WEEK 6 W to WEEK 8 T
Confirm remaining tablets arrival, quality, and layout | Seydou |  |  | 1 | bar: WEEK 7 F
Schedule electrician for remaining tablet installation | Deanna |  |  | 1 | bar: WEEK 7 F
Install remaining tablets and identify potential issues | Seydou |  |  | 1 | bar: WEEK 7 F
Phase 3 progress meeting | Peta |  |  | 1 | bar: WEEK 8 W
Project plan updates | Peta |  |  | 11 | bar: WEEK 6 M to WEEK 8 F
Milestone 5 - Staff Training
Tablet training with GM's | Seydou, Deanna |  |  | 1 | bar: WEEK 8 R
Draft training content & schedule training with Kitchen Managers | Seydou, Gilly, Alex |  |  | 3 | bar: WEEK 8 F to WEEK 9 T
Pre-training staff meeting at North - introduce tablets | Gilly |  |  | 1 | bar: WEEK 9 M
Pre-training staff meeting at Downtown - introduce tablets | Alex |  |  | 1 | bar: WEEK 9 M
Confirm staff training dates with GM's and update staff calendars | Deanna |  |  | 1 | bar: WEEK 9 T
Complete training content and finalize with GM's | Seydou |  |  | 2 | bar: WEEK 9 T to WEEK 9 W
GM's training staff at respective restaurants | Gilly, Alex |  |  | 3 | bar: WEEK 9 R to WEEK 10 M
Finalize launch day plan | Deanna, Peta |  |  | 1 | bar: WEEK 9 R
Confirm post-dining survey | Peta |  |  | 1 | bar: WEEK 9 F
Phase 4 progess meeting | Peta |  |  | 1 | bar: WEEK 10 M
Project plan updates | Peta |  |  | 8 | bar: WEEK 8 R to WEEK 10 M
Milestone 6 - Test Run/Troubleshoot
Team meeting - reviewing contingency plans | Peta, Deanna, GM's, Seydou |  |  | 1 | bar: WEEK 10 T
Test run with family/friends day | Deanna |  |  | 1 | bar: WEEK 10 W
Install upgrades if needed | Seydou |  |  | 2 | bar: WEEK 10 R to WEEK 10 F
Milestone 7 - Launch
Update project plan | Peta |  |  | 3 | bar: WEEK 11 M to WEEK 11 W
Launch day | Deanna |  |  | 1 | bar: WEEK 11 F
Milestone 8 - Project Wrap Up & Closing
Complete closing documentation | Peta |  |  | 2 | bar: WEEK 12 M to WEEK 12 T
Retrospective with stakeholders and restaurant staff | Peta |  |  | 1 | bar: WEEK 12 W

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone 2 - Tablet Sourcing
Research customization options and quotes |  | 4
Find compatible operating systems |  | 3
Confirm top vendors |  | 1
Choose tablet system |  | 2
Establish vendor timeline and deliverables schedule for installation |  | 2
Create contracts and SoW's |  | 5
Milestone 3 - General Project Planning
Create email w/ launch date info for stakeholders |  | 1
Project plan updates |  | 10
Create launch day plan w/ contingencies |  | 2
Create post-dining survey |  | 2
Milestone 5 - Staff Training
Seydou trains GM's | Staff has been resistant to change in the past so training GM's to train staff because the staff is more likely to get on board if someone from the inside trains them | 2 | 3 | 4 | 6 | M
Create and finalize training content with GM's | Small group trainings over multiple days | 3
Staff training | *May be confused with multiple softwares | 3 | 3 | 6 | 8 | L
Finalize launch day plans |  | 1
Milestone 6 - Test Run/Troubleshoot
Test run with real-life scenarios | Family/friends event | 1 | 6 | 6 | 5 | H

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer Satisfaction | Increase customer retention in tablet areas by 5% | Are the tablets producing a better dining experience?
Customer Satisfaction | Average ticket time: 8 min for apps, 12-15 min for entrees | Are the tablets producing efficient ordering between customer and kitchen?
Customer Satisfaction | A one- minute or less checkout time | Do the customers say the tablets are easy to use? Do the tablets save time when the customer is ready to leave?
Customer Satisfaction | Less than 5% of reported technical issues per week | Do the tablets work as expected?
Customer Satisfaction | 98% order accuracy | Are the customers receiving the correct orders as ordered?
Customer Satisfaction | Waitstaff can log on to their tablet on the first try | Are the waitstaff having issues navigating the tablet?

## Survey Questions
Survey Questions
Questions | Question Type | Question Answer Options (depends on question type)
|  | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
How often do you dine with us? | Multiple choice | This was my first time. | I visit every 2-3 months. | I dine with you monthly. | I dine with you weekly. | I dine with you multiple times per week.
Using your best estimation, how long was your entire dining experience? | Multiple choice | Less than 30 minutes | 30 - 45 minutes | 45 - 60 minutes | 60 - 90 minutes | More than 90 minutes
Did you receiving your meal in timely fashion? | Yes/No | Yes | No
Please, rank how easy it was to use the tablet. 1=low ; 5=high | Scaled | 1 | 2 | 3 | 4 | 5
Did you experience any technical issues when ordering or checking out? | Yes/No | Yes | No
Did everyone in your party receive the correct order exactly as it was ordered? | Yes/No | Yes | No
Were you seated within 10 minutes of check-in? | Yes/No | Yes | No
Did you order any of the recommend pairings? | Yes/No | Yes | No
Did you use any discounts or special offers? | Yes/No | Yes | No
Please, rank the features of the tablet. 1=low ; 5=high | Scaled | 1 | 2 | 3 | 4 | 5
Please, rank the likelihood of visiting our restaurant again. 1=low ; 5=high | Scaled | 1 | 2 | 3 | 4 | 5
Please, rank the likelihood of recommending our restaurant with the tablet experience to your friends. 1=low ; 5=high | Scaled | 1 | 2 | 3 | 4 | 5